## Logical Data Modeling Simple
| Conceptual Data Model | Relationships per Concept | Relative Complexity | Hours Effort per Entity | Number of Entities
|  | < = 1 | Very simple | 0.5 | 1 | 0.5
|  | 2 to 3 | Simple | 1 | 2 | 2
|  | 4 to 6 | Medium | 2 | 5 | 10
|  | 7 to 10 | Complex | 4 | 2 | 8
|  | Too Many to Show | Very Complex | 6 | 1 | 6
[5 empty] | 11 | 26.5 | Hours
Logical Data Model | Relationships per Concept | Relative Complexity | Attributes per Entity | Hours Effort per Entity | Number of Entities
| < = 1 | Very simple | < 5 | 2 | 7 | 14
| 2 to 3 | Simple | 5 - 10 | 4 | 5 | 20
| 4 to 6 | Medium | 10 - 15 | 8 | 9 | 72
| 7 to 10 | Complex | 15 - 20 | 16 | 3 | 48
| Too Many to Show | Very Complex | > 20 attributes | 24 | 2 | 48
[5 empty] | 26 | 202 | Total hrs
[6 empty] | 40 | Hrs / week
[6 empty] | 5.05 | Total Work Weeks
[6 empty] | 1 | Resources
[6 empty] | 5.05 | Total Duration in Weeks
Data Estimate
| Logical Data Model | Relative Complexity | Attributes /Entity | Hours Effort/Entity | # of Entities |  | PM Planning
|  | Very simple | < 5 | 2 | 7 | 14
|  | Simple | 5 - 10 | 4 | 5 | 20
|  | Medium | 10 - 15 | 8 | 9 | 72
|  | Complex | 15 - 20 | 16 | 3 | 48
|  | Very Complex | > 20 attributes | 24 | 2 | 48
[6 empty] | 202 | Total hrs
[6 empty] | 2 | Resources
[6 empty] | 101 | Total Duration in Hours
[6 empty] | 40 | Hrs / week
[6 empty] | 2.525 | Work Weeks

## Logical Data Modeling Detailed
| Conceptual Data Model | Relationships per Concept | Relative Complexity | Hours Effort per Entity | Number of Entities
|  | < = 1 | Very simple | 0.5 | 1 | 0.5
|  | 2 to 3 | Simple | 1 | 2 | 2
|  | 4 to 6 | Medium | 2 | 5 | 10
|  | 7 to 10 | Complex | 4 | 2 | 8
|  | Too Many to Show | Very Complex | 6 | 1 | 6
[5 empty] | 11 | 26.5 | Hours
Logical Data Model | Relationships per Concept | Relative Complexity | Attributes per Entity | Hours Effort per Entity | Number of Entities
| < = 1 | Very simple | < 5 | 2 | 31 | 62
| 2 to 3 | Simple | 5 - 10 | 4 | 21 | 84
| 4 to 6 | Medium | 10 - 15 | 8 | 10 | 80
| 7 to 10 | Complex | 15 - 20 | 16 | 1 | 16
| Too Many to Show | Very Complex | > 20 attributes | 24 | 4 | 96
[5 empty] | 67 | 338 | Total hrs
[6 empty] | 40 | Hrs / week
[6 empty] | 8.45 | Total Work Weeks
[6 empty] | 1 | Resources
[6 empty] | 8.45 | Total Duration in Weeks